## 2022 Textiles
|  | DATE APPROVED | 10.14 FINAL | 10.21 FINAL | 6/22 FINAL | 6/21 FINAL | 6/16 FINAL | 6/22 FINAL
|  | Anthro HOME CALENDAR | 2022 | 2022 | 2022 | 2022 | 2022
D47
|  | PRODUCTION MONTH | OCT/NOV/DEC | AUG-DEC | DEC/JAN/FEB | APRIL-JULY | APRIL-JULY
|  | SHIP MONTH - VSL | JAN/FEB | NOV / JAN | MAR/APRIL | JULY/AUG | JULY/AUG
|  | DC RECIEPT MONTH | FEB/MAR | DEC / FEB | March / May | AUG/SEPT | AUG/SEPT
|  | SALES MONTH | MAR/APR | JAN-MAR | MAY/JUNE | SEPT/OCT | SEPT/OCT
Vendor Key Dates | Key Date | Calendar Item | SPRING '22 RUGS | SPRING '22 TEXTILES | SUMMER '22 RUGS + TEXTILES | FALL '22 RUGS | FALL '22 TEXTILES | HOLIDAY '22 TEXTILES
y | y | Concept | 9/21/2020 10/1/2021 | 2020-11-20 | 2021-03-12 | 2021-04-13 | 2021-06-16 | 2021-09-21
|  | Line Plan | 2020-10-08 | 2nd week Jan | 2021-03-22 | 2021-04-15 | 2021-06-09 | 2021-09-23
y |  | Raw Materials Request | 2020-10-02 | 2020-11-05 | 3/1(DESIGN) & 3/15 (CD) | 2021-04-25 | 4/25/2021 raw mats 5/13/21 technique | 2021-09-03
|  | Raw Material X Date | x | 2020-12-31 | 2021-03-29 | 2021-06-18 | 2021-06-18 | 2021-10-22
|  | Raw Materical Showback | 2020-11-30 | 2020-01-12 | - | 2021-06-14 | 2021-06-28 | 2021-10-29
|  | PreSketch w/ PD+Design | 2020-12-04 | 2021-01-31 | 2021-04-19 | 2021-06-21 | 2021-07-15 | 2021-11-04
| y | Sketch Review w/ Home Leaders | wk 12/14 | 2021-02-03 | 2021-04-22 | 2021-06-23 | 2021-07-26 | 2021-11-08
|  | Sketch Review 48hr Feedback return |  |  | N/A | 2021-06-28 | 2021-07-28 | 2021-11-10
|  | Sketch Review Working Sessions |  | 2021-02-09 | 2021-04-26 | 2021-06-17 | 7/30-8/2 | 2021-11-11
|  | Brief Review - Design/PD | 2021-01-31: 2021-03-02; 2021-04-19: N/A
y |  | Proto Brief TPX 1 | 2021-01-21 | - | N/A | 2021-07-21 | N/A | N/A
|  | Proto Brief TPX 2 | 2021-01-28 | - | N/A | N/A | N/A | N/A
|  | Proto Sample Send Date | 2021-02-26 | - | N/A | 2021-09-08 | N/A | N/A
y |  | Proto Overview / Merchandising | 3/16-3/17 | - | N/A | 2021-09-21 | N/A | N/A
|  | Meg Proto | 2021-06-21: 2021-09-22
|  | Proto Working Sessions |  |  | N/A | 2021-09-24 | N/A | N/A
y | y | Finalization Brief TPX 1 | 2021-04-01 | 2021-03-17 | 2021-05-19 | 2021-10-06 | 2021-09-01 | 12/7 - All China Briefs
y |  | Finalization Brief TPX 2 |  | 2021-03-24 | 2021-05-26 | 2021-10-13 | 2021-09-08 | 2021-12-14
y |  | Finalization Brief TPX 3, Prints & Short LT |  |  | 2021-06-02 | N/A | 2021-09-15 | N/A
y |  | Progress Calls/Identify Late Add Styles |  | 2021-04-21 | 2021-06-14 | N/A | 2021-10-01
y |  | Finalization Sample Send Date | 2021-05-25 | 2021-05-05 | 2021-07-12 | 2021-12-10 | 2021-10-25 | 2022-01-18
|  | B17 Room Clean up / Sample transfer |  | 5/6, 5/12 | 2021-07-19 | 2021-12-20 | WK OF 11/1 | 2022-01-25
|  | Finalization Set up (Design+Buying own) |  | 2021-05-13 | 2021-07-22 | 2021-12-20 | WK OF 11/1 | 2022-01-25
y | y | Finalization Exec Review: Meg + Tricia |  | 2021-05-21 | 2021-08-04 | 2022-01-07 | 2021-11-17 | 2022-02-01
| y | Finalization Working Session (2hr mtgs) |  | 5/24, 5/25, 5/26 | 8/5, 8/6, 8/9 | 2022-01-14 | WK OF 11/29 | 2/2-2/4
y | y | Buy Review (+1 Week / WED) (Intent to Buy) | 7/13/2021 (47) | 2021-06-04 | 2021-08-12 | 2022-01-20 | 2021-12-08 | 2022-02-08
| y | Exec Investment Review +1wk / WED |  | 2021-06-08 | 2021-08-17 | 2022-01-25 | 2021-12-13 | 2022-02-15
|  | M1 Ammendments DUE | 2021-01-31: 2021-06-03; 2021-06-21: N/A; 2021-07-15: 2021-12-10
y |  | M2/Chase briefs due |  | 2021-06-03 | 2021-08-15 | N/A | 2021-12-15 | 2022-02-08
y |  | M2/Chase sample X |  | 2021-07-09 | 2021-09-24 | N/A | 2022-01-25 | 2022-03-07
|  | M2 Working Sessions |  | 2021-07-16 | 2021-10-06 | N/A | 2022-02-01 | 2022-03-14
LARGE FORMAT
|  | POHO: LF 120D COMMIT DUE DATE | 2021-05-27 | TBD | TBD | 2022-01-10 | TBD
|  | POHO: LF 90D COMMIT DUE DATE | 2021-06-26 | TBD | TBD | 2022-02-12 | TBD | TBD
|  | HO DATE: LF VSL | 2021-09-24 | TBD | TBD | 2022-05-13 | TBD | TBD
|  | NDC DATE: LARGE FORMAT | 2021-12-13 | TBD | TBD | 2022-08-01 | TBD | TBD
Month 1
y | y | POHO: M1 120D COMMIT DUE DATE | 2021-05-30 | 2021-05-27 | 2021-08-19 | 2021-11-17 | 2021-12-15 | 2022-02-16
|  | POHO: M1 90D COMMIT DUE DATE | 2021-06-29 | 2021-06-26 | 2021-09-26 | 2021-12-17 | 2022-01-16 | 2022-03-22
y | y | HO DATE: M1 VSL | 2021-09-27 | 2021-09-24 | 2021-12-25 | 2022-03-17 | 2022-04-16 | 2022-06-20
| y | NDC DATE: MONTH 1 | 2021-12-13 | 2021-12-13 | 2022-03-15 | 2022-06-05 | 2022-07-05 | 2022-09-05
Month 2
y |  | POHO: M2 120D COMMIT DUE DATE | 2021-07-11 | 2021-07-20 | 2021-10-10 | 2022-01-27 | 2022-01-20 | 2022-03-15
|  | POHO: M2 90D COMMIT DUE DATE | 2021-08-10 | 2021-08-19 | 2021-11-09 | 2022-02-26 | 2022-02-19 | 2022-04-12
y |  | HO DATE: M2 VSL | 2021-11-08 | 2021-11-17 | 2022-02-07 | 2022-05-27 | 2022-05-20 | 2022-07-11
|  | NDC DATE: MONTH 2 | 2022-01-27 | 2022-02-05 | 2022-04-28 | 2022-08-15 | 2022-08-08 | 2022-09-26
Note on G16: Lauren Hunter: design wants 6/7
Note on G17: Lauren Hunter: feedbak 6/10
Note on E38: Lauren Hunter: was 6/16

## 2022 F&D (hidden)
SPRING 2022 FURNITURE LIGHTING & DÉCOR CALENDAR |  |  | FALL 2022 FURNITURE LIGHTING & DÉCOR CALENDAR
SPRING 2020 | SPRING 2022 (Week of) | Notes | FALL22 | FALL 2022 (Week of) | Notes
Predevelopment Requests | 2020-08-21 | Focused on upholstery but all materials & finishes can be requested here. R&D will be done on a rolling basis. | Predevelopment Requests | 2021-03-15
Early "Core" Line Plan | 2020-08-31 | Design Team will be ready to start working 2-3 weeks before concept. Also can sketch ideas to put into concept. | Early "Core" Line Plan
LINE PLAN & CONCEPT |  |  | LINE PLAN & CONCEPT
Concept Presentation | 2020-09-21 |  | Concept Presentation | 2021-04-12
Line Plan | 2020-09-21 |  | Line Plan | 2021-04-12
Design works on line plan ideation, materials & finishes | 9/21-9/28 |  | Design works on line plan ideation, materials & finishes | 2021-04-19
Design/ Line Plan /Materials & Finishes Alignment | 2020-09-28 | Crossfunctional Meetings | Design/ Line Plan /Materials & Finishes Alignment | 2021-04-19
BRIEF CREATION |  |  | BRIEF CREATION
Initial Sketch Creation (Furniture, Lighting & Décor) | 9/21/20-10/30/20 | 6 weeks from Concept | Initial Sketch (Upholstery) w/ Home Leaders | 2021-05-24 | *ALL Upholstery Briefs due 7/2/2021
Initial Sketch Review Furniture w/ Meg | 2020-11-02 |  | Sketch Review 1 (ROUGH) w/Home Leaders | 2021-05-24 | *** MOVE TO WEEK OF 6/7/2021
Initial Sketch Review w/ Crossfunctional Team | 2020-11-09 | !00% LP Reviewed Here | Sketch Review 2 (RENDERED)w/ Home Leaders | 2021-07-05 | * Room Sets, Upholstery Assignment to Shapes to be confirmed here. * LOUIE on Vacation July 12-24th, Back on July 26th.
Brief Creation | 11/9/20-1/15/21 | 10 weeks total (china & vietnam must be prioritized.) | Brief Creation | 7/5-8/2
Cross Functional Brief Review | 11/16/20-1/15/21 | rolling, to be reviewed in crossfuctional meetings as briefs go out | Cross Functional Brief Review
Briefs Due 1 | 2020-11-20 | Friday | Briefs Due 1 | 2021-07-12 | Friday
Briefs Due 2 | 2020-12-04 | Friday | Briefs Due 2 | 2021-07-19 | Friday
Briefs Due 3 | 2020-12-11 | Friday | Briefs Due 3 | 2021-07-26 | Friday
Briefs Due 4 | 2020-12-18 | Friday | Briefs Due 4 | 8/2/2021 (DUE 8/6) | Friday
Briefs Due 5 | 2020-01-08 | Friday
Briefs Due 6 | 2020-01-15 | Friday
Final Briefs Out (china & vietnam) | 2020-12-14 | absolute last date China & Vietnam briefs can go out | Final Briefs Out (china & vietnam) | X | absolute last date China & Vietnam briefs can go out
Zoom Review of Briefs | approx 3 days later ^ |  | Zoom Review of Briefs | approx 3 days later ^
Final Briefs Out (non china) | 2021-01-15 | absolute last date non China briefs can go out | Final Briefs Out - ALL VENDORS | X | absolute last date non China briefs can go out
Zoom Review of Briefs | approx 3 days later ^ |  | Zoom Review of Briefs | X
PROTO |  |  | PROTO
Swatches/Strikeoff Due To Send Upholstery from Vendors | 2021-01-11 |  | Swatches/Strikeoff Due To Send Upholstery from Vendors
Upholstery Proto | 2021-01-18 | review swatches & yardage with crossfunctional teams. Rendered on Shape, not full samples. Align on Shapes to proceed. | Upholstery Proto
Upholstery Proto Recap | 2021-03-01 |  | Upholstery Proto Recap
Upholstery Yardage Assignment | 2021-03-15 | Determine shapes we want sampled with fabric | Upholstery Yardage Assignment | 2021-07-30
Zoom Proto Review | 2021-03-01 | doesn't need to be 100% finished sampled, revisions can happen on calls. | Zoom Proto Review
FINALIZATION & INVESTMENT REVIEW |  |  | FINALIZATION & INVESTMENT REVIEW
Vendor ships Furniture Final Samples | 2021-04-01 |  | Vendor ships Furniture Final Samples | 2021-09-13
Furniture Samples arrive to Anthro | 2021-05-20 |  | Furniture Samples arrive to Anthro | 2021-11-15
Finalization Set Up | 5/20/21-6/4/21 |  | Finalization Set Up | 11/15-12/3
Finalization | 6/5/21- 6/15/21 |  | Finalization | 2021-12-06
Finalization Exec Review | 2021-06-23 |  | Finalization Exec Review | 2022-01-15
Leader Investment Review Prep | 2021-07-01 |  | Leader Investment Review Prep | 2022-01-20
Exec Investment Review (same as reg calendar) | 2021-07-12 |  | Exec Investment Review (same as reg calendar) | 2022-01-25
INVESTMENT AND ORDER DUE |  |  | INVESTMENT AND ORDER DUE
Top Investments Due from buying to merch | 2021-06-27 |  | Top Investments Due from buying to merch | 2022-02-01
Top Investments Due from buying to merch Upholstery |  |  | POs Due | 2022-02-15 | could be 8/17 but needs to be early because LF, all info/PO for LF & bulk due here
Sample Request due from merch to buying |  |  | SP 120 LF Orders Due in System (Intl) | 2022-01-15
Sample Request due from merch to buying Upholstery |  |  | SHIP DATES
Sample Requests due to Production |  |  | SP LF Ship Date | 2022-05-30
Sample Requests due to Production Upholstery |  |  | SP LF INDC Window | 06/20/2022-07/10/2022
POs Due | 2021-07-20 | could be 8/17 but needs to be early because LF, all info/PO for LF & bulk due here | POs Due | 2021-01-03
POs Due Upholstery |  |  | SP Desired 1st bulk ship date | 2022-06-20
Styleout Begins (with existing samples) |  |  | SP Desired Bulk INDC Window | 08/05/2022-08/25/2022
New/Duplicate Samples Arrive to Anthro |  |  | SP Web Launch | 2022-08-15
Final Showback (late sample & duplicate arrival deadline)
Pack Week
Product Travel
Shoot Dates
In Home Date
SP 120 LF Orders Due in System (Intl) | 2021-07-08 |  | SP 120 LF Orders Due in System (Intl)
SP 120 Orders Due in System (Intl) | 2021-07-08 |  | SHIP DATES
SHIP DATES |  |  | SP LF Ship Date
SP LF Ship Date | 2021-11-10 |  | SP LF INDC Window | 06/20/2022-07/10/2022
SP LF INDC Window | 12/07/2021-12/21/2021 |  | SP LF Store Setup | 08/10/2021-08/25/2022
SP LF Store Setup | 01/27/2021-02/18/2022 |  | SP Desired 1st bulk ship date | 2022-06-20
SP Desired 1st bulk ship date | 2021-12-17 |  | SP Desired Bulk INDC Window | 08/05/2022-08/25/2022
SP Desired Bulk INDC Window | 02/05/2022-02/25/2022 |  | SP Web Launch | 2022-08-15
SP Web Launch | 2022-01-30
SP22 Furniture & Decor FINALIZATION (Updated 3/1/2021)
Miletstone | Date | Notes
Samples X | 4/1/2021 (week)
Samples arrive at Anthro | 5/20/2021-6/1/2021
Set up | 6/1/2021 - 6/14/2021 | Apprx 2 weeks, consider Memorial Day (office closed Mon)
Home Leader Preview | 6/14/2021 or 6/15/2021 | Home Leaders walkthrough w/MB
HS Preview | 6/16/2021, 6/17/2021 or 6/18/2021 | MB, LH, JM, HG walkthrough w/ HS
Finalization Working Sessions | 6/21/2021- 6/29/2021 | PD, Design, Merchants
Exec Review | 7/5/2021 (week) | HS & MH walkthrough w/ MB, LH, JM, HG, need to consider 4th of July (office closed Mon)
Leader Investment Review Prep | 7/5/2021 (week) | (office closed Mon)
Exec Investment Review | 2021-07-09 | HS, MB, Merchants
100% Sample Arrivals For Marketing at Anthro | 2021-09-29

## 2022 F&D
|  |  | Furniture, Lighting, Mirrors, Wall Storage, Bath Hardware | Upholstery | Lampshades, Wallpaper, Wall Art, Baskets, Bath Accessories, Frames
Home Calendar | SPRING 2022 (Week of) | Notes | FALL 2022 (Week of) | FALL 2022 (Week of) | FALL 2022 (Week of) | Notes
Predevelopment Requests | 2020-08-21 | Focused on upholstery but all materials & finishes can be requested here. R&D will be done on a rolling basis. | 2021-03-15
Early "Core" Line Plan | 2020-08-31 | Design Team will be ready to start working 2-3 weeks before concept. Also can sketch ideas to put into concept. |  |  |  | * ADD NUMBER OF WEEKS IN THIS COLOMN
LINE PLAN & CONCEPT
Concept Presentation | 2020-09-21 |  | 2021-04-12 | 2021-04-12 | 2021-04-12
Line Plan | 2020-09-21 |  | 2021-04-12 | 2021-04-12 | 4/12/2021 (relook at this date--- to regroup on business needs)
Design works on line plan ideation, materials & finishes | 9/21-9/28 |  | 2021-04-19 | 2021-04-19
Design/ Line Plan /Materials & Finishes Alignment | 2020-09-28 | Crossfunctional Meetings | 2021-04-19
BRIEF CREATION
Initial Sketch Creation | 9/21/20-10/30/20 | 6 weeks from Concept | 4/12- 6/7 | 4/12-5/10 | 7/26-8/9
Sketch Review 1 (ROUGH) w/Home Leaders | 2020-11-02 |  | 2021-06-07 | X | X
Sketch Review 2 (RENDERED) w/ Home Leaders | 2020-11-09 | 100% LP Reviewed Here | 2021-07-05 | 2021-05-10 | 2021-08-09 | * Room Sets, Upholstery Assignment to Shapes to be confirmed here. * LOUIE on Vacation July 12-24th, Back on July 26th.
Brief Creation | 11/9/20-1/15/21 | 10 weeks total (China & Vietnam must be prioritized.) | 7/5-8/2 | 5/10-6/4 | 7/26-9/3 | *** ADD HS SKETCH PREVIEW AFTER SKETCH 2
Cross Functional Brief Review | 11/16/20-1/15/21 | rolling, to be reviewed in crossfuctional meetings as briefs go out
Briefs Due 1 | 2020-11-20 | Friday | 2021-07-15 | 2021-05-20 | 2021-08-19 | PRIORITIZE CASEGOODS BRIEFS
Briefs Due 2 | 2020-12-04 | Friday | 2021-07-22 | 2021-05-27 | 2021-08-26 | PRIORITIZE CASEGOODS BRIEFS
Briefs Due 3 | 2020-12-11 | Friday | 2021-07-29 | 2021-06-03 | 2021-09-02 | UPHOLSTERY BRIEFS
Briefs Due 4 | 2020-12-18 | Friday | 2021-08-05 |  |  | UPHOLSTERY BRIEFS
Briefs Due 5 | 2020-01-08 | Friday | X
Briefs Due 6 | 2020-01-15 | Friday | X
Final Briefs Out (china & vietnam) | 2020-12-14 | absolute last date China & Vietnam briefs can go out | X
Zoom Review of Briefs | approx 3 days later ^ |  | approx 3 days later ^
Final Briefs Out (non china) | 2021-01-15 | absolute last date non China briefs can go out | X
Zoom Review of Briefs | approx 3 days later ^ |  | X
PROTO
Swatches/Strikeoff Due To Send Upholstery from Vendors | 2021-01-11
Upholstery Proto | 2021-01-18 | review swatches & yardage with crossfunctional teams. Rendered on Shape, not full samples. Align on Shapes to proceed. |  | 2021-07-12
Upholstery Proto Recap | 2021-03-01 |  |  | 2021-07-19
Upholstery Yardage Assignment | 2021-03-15 | Determine shapes we want sampled with fabric |  | 2021-07-26 |  | FINAL ROOM SET SIGNOFF
Zoom Proto Review | 2021-03-01 | doesn't need to be 100% finished sampled, revisions can happen on calls.
FINALIZATION & INVESTMENT REVIEW
Vendor ships Furniture Final Samples | 2021-04-01 |  | 2021-09-13
Furniture Samples arrive to Anthro | 2021-05-20 |  | 2021-11-15
Finalization Set Up | 5/20/21-6/4/21 |  | 11/15-12/3
Finalization | 6/5/21- 6/15/21 |  | 2021-12-06
Finalization Exec Review | 2021-06-23 |  | 2022-01-15 |  |  | ** ADD HS PREVIEW WEEK BEFORE XMAS
Leader Investment Review Prep | 2021-07-01 |  | 2022-01-20
Exec Investment Review (same as reg calendar) | 2021-07-12 |  | 2022-01-25
INVESTMENT AND ORDER DUE
Top Investments Due from buying to merch | 2021-06-27 |  | 2022-02-01
Top Investments Due from buying to merch Upholstery |  |  | 2022-02-15 |  |  | could be 8/17 but needs to be early because LF, all info/PO for LF & bulk due here
Sample Request due from merch to buying |  |  | 2022-01-15
Sample Request due from merch to buying Upholstery
Sample Requests due to Production |  |  | 2022-05-30
Sample Requests due to Production Upholstery |  |  | 06/20/2022-07/10/2022
POs Due | 2021-07-20 | could be 8/17 but needs to be early because LF, all info/PO for LF & bulk due here | 2021-01-03
POs Due Upholstery |  |  | 2022-06-20
Styleout Begins (with existing samples) |  |  | 08/05/2022-08/25/2022
New/Duplicate Samples Arrive to Anthro |  |  | 2022-08-15
Final Showback (late sample & duplicate arrival deadline)
Pack Week
Product Travel
Shoot Dates
In Home Date
SP 120 LF Orders Due in System (Intl) | 2021-07-08
SP 120 Orders Due in System (Intl) | 2021-07-08
SHIP DATES
SP LF Ship Date | 2021-11-10 |  | 06/20/2022-07/10/2022
SP LF INDC Window | 12/07/2021-12/21/2021 |  | 08/10/2021-08/25/2022
SP LF Store Setup | 01/27/2021-02/18/2022 |  | 2022-06-20
SP Desired 1st bulk ship date | 2021-12-17 |  | 08/05/2022-08/25/2022
SP Desired Bulk INDC Window | 02/05/2022-02/25/2022 |  | 2022-08-15
SP Web Launch | 2022-01-30
SP22 Furniture & Decor FINALIZATION (Updated 3/1/2021)
Miletstone | Date | Notes
Samples X | 4/1/2021 (week)
Samples arrive at Anthro | 5/20/2021-6/1/2021
Set up | 6/1/2021 - 6/14/2021 | Apprx 2 weeks, consider Memorial Day (office closed Mon)
Home Leader Preview | 6/14/2021 or 6/15/2021 | Home Leaders walkthrough w/MB
HS Preview | 6/16/2021, 6/17/2021 or 6/18/2021 | MB, LH, JM, HG walkthrough w/ HS
Finalization Working Sessions | 6/21/2021- 6/29/2021 | PD, Design, Merchants
Exec Review | 7/5/2021 (week) | HS & MH walkthrough w/ MB, LH, JM, HG, need to consider 4th of July (office closed Mon)
Leader Investment Review Prep | 7/5/2021 (week) | (office closed Mon)
Exec Investment Review | 2021-07-09 | HS, MB, Merchants
100% Sample Arrivals For Marketing at Anthro | 2021-09-29

## 2022 Trim G&E
Tr | G&E Hardgoods 2021 Calendar : Trim
| Year | 2022 | 2022
| Seasons | Trim | Trim
| PRODUCTION MONTH | APR/MAY/JUNE | FALL 2022
Go back to Table of Contents | SHIP MONTH - VSL | JULY/AUG
| DC RECIEPT MONTH | AUG/SEPT
Cell Formatting Legend | SALES MONTH | SEPT/OCT
Phase | Calendar Item | Trim 2022 | calendar in weeks
pre concept R&D alignment
| concept | 2021-07-19 | 59
| Line plan | 2021-07-21
| R&D presentation | 2021-07-27
| Sketch | august 16th
| 1st round of samples : brief out date | 2021-09-13
| 1st round of samples : vendor sample send dates | 2021-11-01
| 1st round of samples : set-up | 2021-11-08
| 1st round of samples: working session | 2021-11-11
| Briefs out date for finalization | week of 12/6/2021
| vendor sample send dates for Finalization | 2022-01-17
| G&E HG- Finalization Set up | 2022-01-21
| (New) Leader Finalization Preview (Mon PM ) | 2022-01-24
| Leader Alignment (Mary Beth Preview) (Tues) | 2022-01-25
| Finalization Exec Preview - Tricia (Thursday) | 2022-01-27
| (New) Finalization Exec Meg/Hillary (Tues) | 2022-02-01
| G&E HG- working sessions | week of Feb 7th
G&E HG- buy reviews
| Month 1 | Trim
| G&E HG- POHO and approvals due for 120 days M1 | 2022-02-15
| G&E HG- Orders in the system for 120 days M1 | 2022-02-22
| G&E HG- POHO and approvals due for 90 days M1 | 2022-03-11
| G&E HG- Orders in the system for 90 days M1 | 2022-03-22
| G&E HG- Ship date M1 | 2022-06-20
| G&E HG- INDC dates M1 | 2022-09-05
| G&E HG- In-store dates M1 | 2022-10-10
| stage of sampling | phase development | adoption rate goal
| 1st round of samples | 70% of LP, excluding 21 letters of monogram | 65%
| 2nd round of samples | rest of the line plan, excludes 21 letters of monogram | 75%
no chase after finalization , rest of monogram letters and amendments
Note on D15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: extended sampling time due to Golden week
Note on D17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9/22/2021 Textiles R&D presentation

## 2022 G&E
G&E Hardgoods 2022 Calendar
| Year | 2022 | 2022 | 2022 |  |  | 2022 | 2022 | 2022 | 2022
| Seasons | SPRING | SUMMER | Summer new mold for acrylic and Melamine (Tabletop only) |  |  | FALL 2022 | calendar in weeks | HOLIDAY 2022 | calendar in weeks
Phase | Calendar Item | SPRING 2022 | SUMMER 2022 |  |  |  | FALL 2022 | FALL 2022 | HOLIDAY 2022 | HOLIDAY 2022
| pre concept R&D alignment | 2020-12-07 | 2021-02-26 | Deadline for Direction | Feb 17th |  | 2021-04-20 |  | 2021-08-02
| concept | 2020-11-20 | 2021-03-12 |  |  |  | 2021-06-18 | 49.7143 | 2021-08-30 | 53
| Line plan | 2020-12-02 | 2021-03-12 | (Paul)Designer to review request and Provide SW files by | Feb 28th |  | 2021-05-11 |  | 2021-09-01
| R&D presentation | 2021-01-18 | 2021-04-08 |  |  |  | 2021-06-15 |  | 2021-10-06
| Sketch | end of Jan | 2021-04-22 |  |  |  | 2021-07-16 | 45.7143 | 2021-10-20 | 45.7143
| Briefs out date | 2021-03-04 | 2021-05-20 | Costing provided by : | March 9th |  | 2021-07-30 | 43.7143 | 2021-12-01 | 39.7143
| vendor sample send dates for Finalization | 2021-05-05 | 2021-07-01 | All pricing approved and packaging finalized by | March 16th |  | 2021-09-13 |  | 1/12/2022 (ship after CNY)
| G&E HG- Finalization Set up | 2021-05-13 | 7/8 and 7/9 (Thursday and Friday) | Anthro team to review and Provide approval to move forward by: (Hand Mold Requested) | March 23rd |  | 9/30 and 10/1 |  | 2022-01-21
| (New) Leader Finalization Preview (Mon PM ) | 2021-05-17 |  |  |  |  | 2021-10-04 |  | 2022-01-24
| Leader Alignment (Mary Beth Preview) (Tues) | 2021-05-18 |  |  |  |  | 2021-10-05 |  | 2022-01-25
| Finalization Exec Preview -MH and Tricia (Thursday) | 5/20/2021 | 2021-07-21 |  |  |  | 2021-10-07 |  | 2022-01-27 | 31.5714
| G&E HG- working sessions | Week of 5/24 | 7/22, 7/23, 26, 27 | Hand Molds Approved by: (Ok to go to real Mold) | April 20th | No changes to mold after approval give to move to new mold | week of Oct 18th |  | week of 31st Jan 2021
| G&E HG- buy reviews | Week of 5/31 (company closed on 5/31) | 7/28, 7/29, 7/30 | (No changes after this point) |  |  | week of Oct 25th |  | week of Feb 7th 2022
| G&E HG - Investment review (Tricia) | [7 empty] | 2022-02-15
| G&E HG - chase list due to design team | 2021-06-07 | 2021-08-03 | First round of samples to ship by: | July 13th |  | 2021-11-01 |  | 2022-02-12
| G&E HG- Chase briefs due from design to PD | 2021-06-29 | 2021-08-24 |  |  |  | 2021-11-15 |  | 2022-03-04
| G&E HG : Chase Samples due from vendors | 2021-08-09 | 2021-10-01 |  |  |  | 2021-12-23 |  | 2022-04-05
| Month 1 | Spring 1 | Summer 1 (China only, pre CNY) |  |  |  | BTS |  | Early Holiday
| G&E HG- POHO and approvals due for 120 days M1 | 2021-06-08 | 2021-08-30 |  |  |  | 11/5/2021 for India. 11/17/2021 for all COO | 25.8571 | 2022-02-18 | 28
| G&E HG- Orders in the system for 120 days M1 ( po hand back) | 2021-06-16 | 2021-09-13 |  |  |  | 11/16/2021 for India. 12/2/2021 for all COO | 2021-12-02 | 2022-02-21
| G&E HG- POHO and approvals due for 90 days M1 | 2021-07-01 | 2021-10-01 |  |  |  | 11/19/2021 for China & Vietnam. 12/12/2021 for all COO |  | 2022-03-15
| G&E HG- Orders in the system for 90 days M1 (po hand back) | 2021-07-16 | 2021-10-12 |  |  |  | 12/2/2021 for China & Vietnam. 12/22/2021 for all COO. |  | 2022-03-22
| G&E HG- Ship date M1 | 2021-10-14 | 2022-01-10 |  |  |  | 3/16/2022 for India. 4/1/2022 for all COO. |  | 2022-06-20
| G&E HG- INDC dates M1 | 2021-12-13 | 2022-03-01 |  |  |  | 2022-06-01 |  | 2022-09-05
| G&E HG- In-store dates M1 | 2021-01-17 | 2022-03-22 |  |  |  | 2022-07-05 |  | 2022-10-10
| Month 2 | Spring 2 | Summer 2 |  |  |  | Fall 1 |  | Holiday
| G&E HG- POHO and approvals due for 120 days M2 | 2021-07-01 | 2021-08-31 |  |  |  | 2021-11-30 |  | 2022-03-04
| G&E HG- Orders in the system for 120 days M2 | 2021-07-16 | 2021-09-15 |  |  |  | 2021-12-13 |  | 2022-03-14
| G&E HG- POHO and approvals due for 90 days M2 | 2021-08-20 | 2021-10-04 |  |  |  | 1/5/2022 for China and Vietnam. 1/17/2022 for all COO |  | 2022-04-01
| G&E HG- Orders in the system for 90 days M2 | 2021-09-01 | 2021-10-13 |  |  |  | 1/17/2022 for China and Vietnam. 1/27/2022 for all COO |  | 2022-04-12
| G&E HG- Ship date M2 | 2021-12-03 | 1/11/2022 for other COO. No China or Vietnam delivery |  |  |  | 4/11/2022 for India. 4/27/2022 for all COO |  | 2022-07-11
| G&E HG- INDC dates M2 | 2022-02-01 | 2022-03-14 |  |  |  | 2022-06-27 |  | 2022-09-26
| G&E HG- In-store dates M2 | 2022-02-28 | 2022-04-11 |  |  |  | 2022-08-02 |  | 2022-10-31
| Month 3 |  | Fall Trans |  |  |  | Fall 2 |  | Dec Refresh
| G&E HG- POHO and approvals due for 120 days M3 |  | 2021-10-15 |  |  |  | 1/4/2022 for China & India. 1/28/2022 for all COO. |  | 2022-03-25
| G&E HG- Orders in the system for 120 days M3 |  | 2021-10-25 |  |  |  | 1/11/2022 for China & India. 2/8/2022 for all COO. |  | 2022-04-04
| G&E HG- POHO and approvals due for 90 days M3 |  | 11/15/2021 for all COO. 10/15/2021 for China and Vietnam |  |  |  | 2022-02-28 |  | 2022-04-22
| G&E HG- Orders in the system for 90 days M3 |  | 11/24/2021 for all COO. 10/25/2021 for China and Vietnam |  |  |  | 2022-03-10 |  | 2022-05-03
| G&E HG- Ship date M3 |  | 2022-02-22 |  |  |  | 5/23/2022 for India. 6/8/2022 for all COO |  | 2022-08-01
| G&E HG- INDC dates M3 |  | 2022-04-25 |  |  |  | 2022-08-08 |  | 2022-10-17
| G&E HG- In-store dates M3 |  | 2022-05-31 |  |  |  | 2022-09-13 |  | 2022-11-21
| creative marketing sample request due | 2021-06-08 | 2021-08-30 |  |  |  | 2021-11-05
| creative marketing sample request due to PD | 2021-06-22 | 2021-09-13 |  |  |  | 2021-11-05
| creative marketing vendor send dates | 2021-09-24 | 2021-11-05 |  |  |  | 2022-04-08
| creative marketing samples due | 2021-10-04 | 2021-11-15 |  |  |  | 2022-04-18
Spring 2 2022 : Chase cadence by COO
Only Spring 2 chase allowed. Spring 1 cannot be chased.
Portugal : We can check production space, if not available, we will have to source with China.
India : Other than Stalwarts, cannot chase with any other vendors. This is true for Spring 2 as well.
Stalwarts : Existing shape and existing technique, can achieve Spring 2 chase. Fragrances will need to be ordered as part of 120 days LT.
Aromabay : Can chase Spring 2 for shaped wax.
Stationary : can chase with China for Spring 2. Cannot chase with India for Spring 1 or 2.
Summer 2022 :
Bamboo and acrylic : approvals due 9/1, due to increased raw material lead times
Formulas:
FALL 2022 = ([FALL 2022, row below]-14)
FALL 2022 = ([FALL 2022, row above]+14)
HOLIDAY 2022 = ([HOLIDAY 2022, row below]-42)
SUMMER = ([SUMMER, row above]+42)
SUMMER = ([SUMMER, row below]-21)
SPRING = ([SPRING, row above]+14)
SPRING = ([SPRING, row below]-10)
Note on I6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: happened 5/10/2021
Note on J6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: concept to INDC
Note on L6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: concept to INDC
Note on J9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: sketch to INDC
Note on L9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: sketch to INDC
Note on D10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: same as textiles
Note on J10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: brief out to INDC
Note on L10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: brief out to INDC
Note on L15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: finalization to INDC
Note on D20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No chase allowed for Spring 1.
Note on E20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: only Fall Trans chase allowed
Note on I20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No chase allowed for BTS & Fall 1 120 days
Note on K20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: no chase allowed for early holiday and 120 days true holiday
Note on E24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: extended due to holidays
Note on I24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: extended to accomadate holidays
Note on J24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: POHB to INDC
Note on L24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: POHB to INDC
Note on D26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: added lead times for holidays
Note on I27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: extended to accomadate holidays
Note on I33: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: extended to accomadate holidays

## OLD - 2022 Textiles (hidden)
|  |  |  | 10.14 FINAL | 10.21 FINAL | 12.1 Draft | 1.29 FINAL | 3/26 REVISED | 12.3 Draft | 1.20 draft
|  |  | Anthro HOME CALENDAR | 2022 | 2022 | 2022 | 2022 | 2022 | 2022 | 2022 | 10/28 Mtg notes
|  |  |  | SPRING- RUGS | SPRING- Textiles | Summer Textiles | Summer Textiles | Summer Textiles | FALL - Rugs | FALL - Textiles
D47
|  |  | PRODUCTION MONTH | OCT/NOV/DEC | AUG-DEC | DEC/JAN/FEB | DEC/JAN/FEB | DEC/JAN/FEB | APRIL-JULY | APRIL-JULY
|  |  | SHIP MONTH - VSL | JAN/FEB | NOV / JAN | MAR/APRIL | MAR/APRIL | MAR/APRIL | JULY/AUG | JULY/AUG
|  |  | DC RECIEPT MONTH | FEB/MAR | DEC / FEB | March / May | March / May | March / May | AUG/SEPT | AUG/SEPT
SP | SUM |  | SALES MONTH | MAR/APR | JAN-MAR | MAY/JUNE | MAY/JUNE | MAY/JUNE | SEPT/OCT | SEPT/OCT
|  | Phase | Calendar Item
117 | 41 | PREDEV | Concept | 9/21/2020 10/1/2021 | 2020-11-20 | 2020-01-12 | 2021-03-12 | 2021-03-12 | 2021-04-21 | 2021-05-20 | 111
|  | PREDEV | Line Plan | 2020-10-08 | 2nd week Jan | 2020-01-12 | 2021-03-22 | 2021-03-22 | 2021-04-21 | 2021-05-23
|  | PREDEV | PreDev Raw materials Request | 2020-10-02 | 2020-11-05 | 2020-01-19 | 2/5 - ACTUAL 3/1 Tgt CD 3/15 | 2/5 - ACTUAL 3/1 Tgt CD 3/15 | 2021-04-28 | 4/25/2021 raw mats 5/25/21 technique
|  | PREDEV | Predevelopment x | x | 2020-12-31 | 2020-03-04 | 3/22 - Revised 3/29 | 3/22 - Revised 3/29 | 2021-06-12 | 2021-07-10
|  | PREDEV | PreDev Showback PD / Design, PD / Buying | 2020-11-30 | 2020-01-12 | 2020-03-11 | 3/29 - now eliminate | 3/29 - now eliminate | 2021-06-19 | 7/20/2021 - consolidate with 7/26 showback
|  | PREDEV | Seasonal Fabric Story (Start long lead bases) | x | 2021-01-21 | 2020-03-18 | 2021-04-19 | 2021-04-19 | 2021-06-26 | 7/26/2021 make this 7/20 | Initial Hindsight/Sales Reads
|  | SKETCH | PreSketch w/ PD+Design | 2020-12-04 | 2021-01-31 | 2020-04-01 | 2021-04-19 | 2021-04-19 | 2021-07-10 | 2021-08-04
|  | SKETCH | Sketch w/Meg | wk 12/14 | 2021-02-03 | 2020-04-03 | 2021-04-22 | 2021-04-22 | 2021-07-13 | 2021-08-07 | 362 | 334
36 | 23 | SKETCH | Sketch Review w/Buying |  | 2021-02-09 | 2020-04-15 | 2021-04-26 | 2021-04-26 | 2022-07-20 | 2021-08-11
307 |  | SKETCH | Sketch with HS |  | 2021-02-18
|  | SKETCH | Sketch Wrap on cost issues with Carrie, Brittany, Lauren |  | 2021-02-19
|  | DEVELOPMENT | Brief Review - Design/PD |  | 2021-03-02 | 2021-05-14 | n/a | n/a | 2022-08-15 | 2021-09-03
|  | DEVELOPMENT | Briefs TPX 1 - All China (due to CNY) | x | x
49 |  | DEVELOPMENT | Briefs TPX 1 | 2021-01-21 | 2021-03-17 | 2021-05-17 | 2021-05-19 | 2021-05-19 | 2022-09-04 | 2021-09-08
|  | DEVELOPMENT | Briefs TPX 2 | 2021-01-28 | 2021-03-24 | 2021-05-27 | 2021-05-26 | 2021-05-26 | 2022-09-14 | 2021-09-15 | Hindsight/Sales Reads
|  | DEVELOPMENT | Briefs TPX 3, Prints & Short LT |  |  | 2021-06-06 | 2021-06-02 | 2021-06-02 | 2022-09-24 | 2021-09-22
|  | DEVELOPMENT | Proto Sample X | 2021-02-26
|  | DEVELOPMENT | Proto Review | 3/16-3/17 | Virtual - WK OF 4/13 | X | WK OF 6/14 | WK OF 6/14
|  | DEVELOPMENT | Rug Proto Brief Date | 2021-04-01 |  | X | X | X
|  | DEVELOPMENT | Sample x | 2021-05-25 | 2021-05-05 | 2021-07-11 | 2021-07-12 | 2021-07-12 | 2022-10-29 | 2021-11-01
|  | DEVELOPMENT | IDENTIFY LATE ADDS |  | 2021-04-21 | 2021-07-11 | 2021-06-14 | 2021-06-14
|  | FINALIZATION | Buyer Merch Assort Sheet Creation / TS Offers Updated | [6 empty] | 2021-11-08
|  | FINALIZATION | B17 Room Clean up / Sample transfer |  | 2021-05-12 | 2021-07-12 | 2021-07-19 | 2021-08-02 |  | 2021-11-08
|  | FINALIZATION | Finalization Set up (Design+Buying own) |  | 2021-05-13 | 2021-07-21 | 2021-07-24 | 2021-08-09 |  | 2021-11-08
|  | FINALIZATION | (New) Leader Finalization Preview (Mon PM ) |  | 2021-05-17 |  |  | 2021-08-16
|  | FINALIZATION | Leader Alignment (Mary Beth Preview) (Tues) |  | 2021-05-18 |  |  | 2021-08-17
|  | FINALIZATION | Finalization Exec Preview - Hillary (Thursday) | 6/5/21- 6/15/21 (47) | 5/20/2021 | 2021-07-25 | 2021-07-26 | 2021-08-19 |  | 2021-11-15
|  | FINALIZATION | (New) Finalization Exec Meg/Hillary (Tues) |  | 2021-05-25 |  |  | 2021-08-24
|  | FINALIZATION | Finalization Working Session (Execs attend first hour) |  | 5/26, 5/27, 6/1 | 2021-08-15 | 2021-08-02 | 8/25, 8/26, 8/27 |  | 2021-11-17
|  | FINALIZATION | Merchandising / Assort + Cost Reports | 6/5/21- 6/15/21 (47) | 2021-05-17 | 2021-07-28 | - | -
|  | FINALIZATION | Intent to Buy |  | n/a | 2021-08-05 | - | -
|  | FINALIZATION | Buy Review (+1 Week / WED) (Intent to Buy) | 7/13/2021 (47) | 2021-06-09 | 2021-08-07 | 2021-08-23 | 2021-09-09 |  | 2021-12-06
|  | FINALIZATION | Exec Investment Review (HillaryS.) +1wk / WED |  | 2021-06-09 | 2021-09-01 | Buying to advise | Buying to advise
|  | FINALIZATION | M1 Ammendments DUE |  | 2021-06-03 | 2021-09-03 |  |  |  | 2021-11-24
|  | FINALIZATION | M2 Chase briefs due |  | 2021-06-16 |  | 2021-08-31 | 2021-08-31 |  | 2021-12-15
|  | FINALIZATION | Chase sample X |  | 2021-07-20 |  | 2021-10-10 | 2021-10-10 |  | 2022-01-25
|  | FINALIZATION | M2 Working Sessions |  | 2021-07-29 |  | 2021-10-18 | 2021-10-18 |  | 2022-02-01
|  | LARGE FORMAT | POHO: LF 120D COMMIT DUE DATE | 2021-06-11 | -185 | -185 | -185 | -185 | -185 | -185
|  | LARGE FORMAT | POHO: LF 90D COMMIT DUE DATE | 2021-07-11 | -155 | -155 | -155 | -155 | -155 | -155
|  | LARGE FORMAT | HO DATE: LF VSL | 2021-10-09 | -65 | -65 | -65 | -65 | -65 | -65
|  | LARGE FORMAT | NDC DATE: LARGE FORMAT | 2021-12-13
|  | M1 | POHO: M1 120D COMMIT DUE DATE | 2021-06-16 | 2021-06-16 | 2020-09-16 | 2021-09-16 | 2021-09-16 | 2021-01-08 | 2022-01-08
|  | M1 | POHO: M1 90D COMMIT DUE DATE | 2021-07-16 | 2021-07-16 | 2020-10-16 | 2021-10-16 | 2021-10-16 | 2021-02-07 | 2022-02-07
|  | M1 | HO DATE: M1 VSL | 2021-10-14 | 2021-10-14 | 2021-01-14 | 2022-01-14 | 2022-01-14 | 2021-05-08 | 2022-05-08
|  | M1 | NDC DATE: MONTH 1 | 2021-12-13 | 2021-12-13 | 2021-03-15 | 2022-03-15 | 2022-03-15 | 2021-07-07 | 2022-07-07
|  | M2 | POHO: M2 120D COMMIT DUE DATE | 2021-07-31 | 2020-08-05 | 2020-10-30 | 2021-10-30 | 2021-10-30 | 2021-02-09 | 2022-02-09
|  | M2 | POHO: M2 90D COMMIT DUE DATE | 2021-08-30 | 2020-09-04 | 2020-11-29 | 2021-11-29 | 2021-11-29 | 2021-03-11 | 2022-03-11
|  | M2 | HO DATE: M2 VSL | 2021-11-28 | 2020-12-03 | 2021-02-27 | 2022-02-27 | 2022-02-27 | 2021-06-09 | 2022-06-09
|  | M2 | NDC DATE: MONTH 2 | 2022-01-27 | 2021-02-01 | 2021-04-28 | 2022-04-28 | 2022-04-28 | 2021-08-08 | 2022-08-08
|  | ORDERS | SP 120 LF Orders Due in System (Intl) | 2021-06-12
|  | ORDERS | POHO- M1 VSL 120 days commits CHINA | x | 2021-06-10 | 2021-09-14 | 2021-09-14 | 2021-09-14 | 2022-01-06
|  | ORDERS | POHO- M1 VSL 120 days commits INDIA / PORTUGAL | 2021-08-03 | 2021-06-10 | 2021-09-14 | 2021-09-14 | 2021-09-14 | 2022-01-06
|  | ORDERS | POHO- M1 VSL 120 days commits Pak/Turkey |  | 2021-07-12 | 2021-09-14 | 2021-09-14 | 2021-09-14 | 2022-01-06
|  | ORDERS | POHO M1 90 day |  | 2021-07-12
|  | ORDERS | POHO M1 90 day |  | 2021-07-12 | 2021-10-14 | 2021-10-14 | 2021-10-14 | 2022-02-05
|  | ORDERS | ALL ORDERS IN SYSTEM FOR M1 - FINAL
|  | ORDERS | M2 Chase Samples due from vendors |  | 2021-07-25
|  | ORDERS | POHO- M2 VSL 120 days commits + Chase Working Sessions |  | 2021-08-01 | 2021-10-26 | 2021-10-26 | 2021-10-26 | 2022-02-05
|  | ORDERS | POHO- M2 VSL 90 days commits |  | 2021-08-31 | 2021-11-25 | 2021-11-25 | 2021-11-25 | 2022-03-07
|  | TRANSIT | LF Ship Date - RUGS
|  | TRANSIT | LF Ship Date | 2021-10-10
|  | TRANSIT | LF DC Date - RUGS / INDIA | 2021-12-13
|  | TRANSIT | LF INDC Window | 12/07/2021-12/21/2021
|  | TRANSIT | LF Store Setup | 01/27/2021-02/18/2022
|  | TRANSIT | Desired 1st bulk ship date | 2021-12-17
|  | TRANSIT | desired Bulk INDC Window | 02/05/2022-02/25/2022
|  | TRANSIT | Web Launch | 2022-01-30
|  | TRANSIT | HO date VSSL (Approx) M1 | 2021-12-11 | 2021-10-10 | 2022-01-12 | 2022-01-12 | 2022-01-12 | 2022-05-06
|  | TRANSIT | MONTH 1 INDC | 2022-02-13 | 2021-12-13 | 2022-03-17 | 2022-03-17 | 2022-03-17 | 2022-07-07
|  | TRANSIT | HO date VSSL (Approx) M2 |  | 2021-11-29 | 2022-02-23 | 2022-02-23 | 2022-02-23 | 2022-06-05
|  | TRANSIT | MONTH 2 INDC |  | 2022-02-01 | 2022-04-28 | 2022-04-28 | 2022-04-28 | 2022-08-08
DIWALI 2020 - NOV 14
DIWALI 2021 - NOV 4
CNY 2021 - 2/1-3/1, 2/12 actual
DC Dates from Nicole Jones FEB8 email
|  |  | Deliveries | DC Date Due - START | DC Date Due - END | 2022 Instore Dates - Mondays
|  |  | SPRING 1 | 2021-12-13 | 2021-12-27 | 2022-01-17
|  |  | SPRING 2 | 2022-02-01 | 2022-02-10 | 2022-02-28
|  |  | SUMMER | 2022-03-14 | 2022-03-24 | 2022-04-11
|  |  | SUMMER REFRESH | 2022-04-25 | 2022-05-09 | 2022-05-31
|  |  | BTS | 2022-06-01 | 2022-06-15 | 2022-07-05
|  |  | FALL 1 | 2022-06-27 | 2022-07-12 | 2022-08-01
|  |  | FALL 2 | 2022-08-08 | 2022-08-23 | 2022-09-12
|  |  | TRIM | 2022-09-05 | 2022-09-15 | 2022-10-10
|  |  | EARLY HOL | 2022-09-05 | 2022-09-15 | 2022-10-10
|  |  | HOLIDAY | 2022-09-26 | 2022-10-06 | 2022-10-31
|  |  | DEC REFRESH | 2022-10-17 | 2022-10-31 | 2022-11-21
Formulas:
Summer Textiles = [Summer Textiles, row below]-7
Summer Textiles = [Summer Textiles, row above]+5
FALL - Rugs = [FALL - Rugs, row below]-7
SPRING- RUGS = [SPRING- RUGS, row below]-90
SPRING- Textiles = [SPRING- Textiles, row below]-90
Note on F10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: proposed on 10/21 Mtg
Note on H11: Lauren Hunter: move out 1wk per NJ request
Note on I11: Lauren Hunter: move out 1wk per NJ request
Note on F12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: add R&D Dates to outlook
Note on G17: Lauren Hunter: pulled up to give more time bt sketch & brief deadline
Note on F18: Lauren Hunter: pushed from 1/15
Note on F25: Lauren Hunter: revised from 3/11
Note on F26: Lauren Hunter: revised from 3/18
Note on F47: Lauren Hunter: pulled up from 6/11 org.
Note on F48: Lauren Hunter: pulled up from 6/25 org.
Note on F49: Lauren Hunter: pulled up from 7/26 org.
Note on F50: Lauren Hunter: pulled up from 8/3 org.

## WEEKS CHART (hidden)
WEEKS TO DC | Apparel | Home Gift & Entertain | Furniture/Décor
Phase 1 | Phase 1 | Phase 1 | Phase 2
Concept to IN DC | 29 | 55 | 70
Sketch to IN DC (average) | 25 | 49 | 58
Spec Pack to IN DC | 24 | 43 | 57
Finalization to IN DC | 17 | 32 | 36
POHO to IN DC | 16 | 28 | 32
Phase 2 | Phase 2 | Chase | Chase
Spec Pack to IN DC | 15 | 26 | x
Order place to IN DC | 11 | 21 | x
Chase
Order place to IN DC | 8 | x | x
WEEKS TO DC | Gift/Entertain/Textiles | Furniture/Décor | Apparel | UO Textiles | UO Hardgoods
Phase 1 | Phase 1 | Phase 1 | Phase 1 | Phase 1 | Phase 1
Concept to IN DC | 55 | 70 | 29 | 39 | 51
Sketch to IN DC (average) | 49 | 58 | 25 | 34 | 46
Spec Pack to IN DC | 43 | 57 | 24 | 33 | 42
Finalization to IN DC | 32 | 36 | 17 | 24 | 25
POHO to IN DC | 28 | 32 | 16 | 22 | 23
Phase 2 | Phase 2 / Chase | Chase | Phase 2
Spec Pack to IN DC | 26 | x | 15 | 25 | x
Order place to IN DC | 21 | x | 11 | 19 | x
Chase
Order place to IN DC | x | x | 8 | 17 | x
Anthro HOME CALENDAR | 2022 |  |  |  | dates are just average will adjust
proposed 5.18 for Tricia/Meg Mtg |  |  |  |  | Textile 1st Proposal | Textile 1st Proposal | Textile 1st Proposal – Cadence
Calendar Item | FALL '22 TEXTILES | Days | Weeks | UO | Textile 1st Proposal | Days | Weeks
Concept | 47 | 385 | 55 | 39 | 2021-08-01 | 330 | 47
Sketch Review w/ Home Leaders | 43 | 342 | 49 | 34 | 2021-09-01 | 299 | 43
Finalization Brief TPX 1 | 38 | 299 | 43 | 33 | 2021-10-01 | 269 | 38
(New) Finalization Exec Meg (Tues) | 30 | 222 | 32 | 24 | 2021-12-01 | 208 | 30
M2 Chase briefs due | 28 | 194 | 28 |  | 2021-12-15 | 194 | 28
POHO: M1 120D COMMIT DUE DATE | 28 | 194 | 28 | 26 | 2021-12-15 | 194 | 28
POHO: M1 90D COMMIT DUE DATE |  | 150 | 22 | 22 | 2022-01-28
HO DATE: M1 VSL | 2022-04-28 |  |  |  | 2022-04-28
NDC DATE: MONTH 1 | 2022-06-27 |  |  |  | 2022-06-27

## proposed weeks (hidden)
Anthro HOME CALENDAR | 2022 |  |  |  | dates are just average will adjust
[5 empty] | Textile 1st Proposal | Textile 1st Proposal | Textile 1st Proposal – Cadence
Calendar Item | FALL '22 TEXTILES | Days | Weeks | UO | Textile 1st Proposal | Days | Weeks
Concept | 2021-06-07 | 385 | 55 | 39 | 2021-08-01 | 330 | 47 | 8
Sketch Review w/ Home Leaders | 2021-07-20 | 342 | 49 | 34 | 2021-09-01 | 299 | 43 | 6
Finalization Brief TPX 1 | 2021-09-01 | 299 | 43 | 33 | 2021-10-01 | 269 | 38 | 5
(New) Finalization Exec Meg (Tues) | 2021-11-17 | 222 | 32 | 24 | 2021-12-01 | 208 | 30 | 2
M2 Chase briefs due | 2021-12-15 | 194 | 28 |  | 2021-12-15 | 194 | 28
POHO: M1 120D COMMIT DUE DATE | 2021-12-15 | 194 | 28 | 26 | 2021-12-15 | 194 | 28
POHO: M1 90D COMMIT DUE DATE | 2022-01-28 | 150 | 22 | 22 | 2022-01-28
HO DATE: M1 VSL | 2022-04-28 |  |  |  | 2022-04-28
NDC DATE: MONTH 1 | 2022-06-27 |  |  |  | 2022-06-27